## Sprint 1
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: | Task: | Planned Effort: | Real Effort: |  | 2 WEEKS
DBS | 14.29 | 16 | 14.29 | 16 | Start | 100 | 100 | done
MVC | 14.29 | 20 | 14.29 | 20 | DBS (system) | 85.71 | 84
View | 14.29 | 16 | 14.29 | 16 | MVC (system) | 71.42 | 64
Domain | 14.29 | 0 | 14.29 | 0 | View (user stories 2 and3) | 57.13 | 39 |  | Backlog 2 and 3
Controller | 14.29 | 0 | 14.29 | 0 | Domain (user stories 2 and3) | 42.84 | 39
Documentation | 14.29 | 4 | 14.29 | 4 | Controller (user stories 2 and3) | 28.55 | 29
Scrum Documentation Sprint 1 | 14.29 | 4 | 14.29 | 4 | Documentation (backlog 2 and3) | 14.26 | 24
Total: | 100.03 | 60 | 100.03 | 60 | Scrum Documentation Sprint 1 | -0.03 | 19
If: | 100 | 100
Then: | 14.29 | 14.29
If: | 40 | 100
Then: | 2 | 5
If: | 40 | 100
Then: | 4 | 10
If: | 40 | 100
Then: | 8 | 20
If: | 40 | 100
Then: | 10 | 25

## Sprint 2
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: | Task: | Planned Effort: | Real Effort: |  | 2 WEEKS
Domain(Backlog 2 and 3) | 11.1 | 0 | 11.1 | 0 | Start | 100 | 100
Controller(Backlog 2 and 3) | 11.1 | 0 | 11.1 | 0 | Domain (user stories 2 and3) | 88.9 | 100 | done
Documentation(backlog 2 and 3) | 11.1 | 0 | 11.1 | 0 | Controller (user stories 2 and3) | 77.8 | 100
DBS2 | 11.1 | 0 | 11.1 | 0 | Documentation (user stories 2 and3) | 66.7 | 100
View (Backlog 1) | 11.1 | 0 | 11.1 | 0 | DBS 2.0 | 55.6 | 100
Domain | 11.1 | 0 | 11.1 | 0 | View (user story 1) | 44.5 | 100
Controller | 11.1 | 0 | 11.1 | 0 | Domain (user story 1) | 33.4 | 100
Documentation | 11.1 | 0 | 11.1 | 0 | Controller (user story 1) | 22.3 | 100
Scrum Documentation | 11.1 |  | 11.1 |  | Documentation (user story 1) | 11.2 | 100
Total: | 100 | 0 | 11.1 | 0 | Scrum documentation Sprint 2 | 0 | 100
If: | 100 | 100
Then: | 11.1 | 11.1

## Sprint 3
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: |  |  | Task: | Planned Effort: | Real Effort: |  | 2 WEEKS
Domain(backlogs 2 and 3) | 11.1 | 12 | 11.1 | 12 | x |  | Start | 100 | 100
Controller(backlogs 2 and 3) | 11.1 | 8 | 11.1 | 8 | x |  | Domain(backlogs 2 and 3) | 88.9 | 88 | done
Documentation(backlogs 2 and 3) | 11.1 | 1 | 11.1 | 1 |  |  | Controller(backlogs 2 and 3) | 77.8 | 80
DBS2 | 11.1 | 16 | 11.1 | 16 | x |  | Documentation(backlogs 2 and 3) | 66.7 | 79
View (backlogs 1) | 11.1 | 12 | 11.1 | 12 | x |  | DBS2 | 55.6 | 63
Domain (backlogs 1) | 11.1 | 6 | 11.1 | 6 | x |  | View (backlogs 1) | 44.5 | 51
Controller (backlogs 1) | 11.1 | 4 | 11.1 | 4 | x |  | Domain (backlogs 1) | 33.4 | 45
Documentation (backlogs 1) | 11.1 | 0.5 | 11.1 | 0.5 |  |  | Controller (backlogs 1) | 22.3 | 41
Scrum Documentation Sprint 3 | 11.1 | 0.5 | 11.1 | 0.5 |  |  | Documentation (backlogs 1) | 11.2 | 40.5
Total: | 99.9 | 60 | 99.9 | 60 |  |  | Scrum Documentation Sprint 3 | 0 | 40
If: | 100 | 100 |  | If: | 100 | 100
Then: | 0.5 | 0.5 |  | Then: | 8 | 8
If: | 100 | 100 |  | If: | 100 | 100
Then: | 4 | 4 |  | Then: | 12 | 12
If: | 100 | 100
Then: | 6 | 6

## Sprint 4
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: |  | Task: | Planned Effort: | Real Effort: |  | 1 WEEK
Implement Controller (User stories 2 and 3) | 5.55 | 6 | 11.1 | 12 |  | Start | 100 | 100 | done
Implement Domain (User stories 2 and 3) | 5.55 | 4 | 11.1 | 8 |  | Implement Controller (User stories 2 and 3) | 88.9 | 88
Documentation (User stories 2 and 3) | 5.55 | 0.5 | 11.1 | 1 |  | Implement Domain (User stories 2 and 3) | 77.8 | 80
Modify DBS | 5.55 | 8 | 11.1 | 16 |  | Documentation (User stories 2 and 3) | 66.7 | 79
View (User story 1) | 5.55 | 12 | 11.1 | 24 |  | Modify DBS | 55.6 | 63
Domain (User story 1) | 5.55 | 6 | 11.1 | 12 |  | View (User story 1) | 44.5 | 39
Controller (User story 1) | 5.55 | 4 | 11.1 | 1 |  | Domain (User story 1) | 33.4 | 27
Documentation (User story 1) | 5.55 | 0.5 | 11.1 | 5 |  | Controller (User story 1) | 22.3 | 26
Scrum Documentation Sprint 4 | 5.55 | 0.5 | 11.1 | 5 |  | Documentation (User story 1) | 11.2 | 21
Total | 49.95 | 41.5 | 99.9 | 84 |  | Scrum Documentation Sprint 4 | 0.1 | 16
If: | 50 | 100 |  | If: | 20 | 100
Then: | 6 | 12 |  | Then: | 8 | 40
If: | 20 | 100 |  | If: | 20 | 100
Then: | 4 | 20 |  | Then: | 12 | 60
If: | 20 | 100 |  | If: | 20 | 100
Then: | 6 | 30 |  | Then: | 2.2 | 11

## Sprint 5
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: |  | Task: | Planned Effort: | Real Effort: |  | 2 DAYS
Analysis User story 1 | 1.43 | 1 | 7.15 | 5 |  | Start | 100 | 100 | done
Design User story 1 | 1.43 | 2 | 7.15 | 10 |  | Analysis User story 1 | 92.85 | 95
Implement User story 1 | 1.43 | 3 | 7.15 | 15 |  | Design User story 1 | 85.7 | 85
Document implementation User Story 1 | 1.43 | 1 | 7.15 | 5 |  | Implement User story 1 | 78.55 | 70
Test User story 1 | 1.43 | 1 | 7.15 | 5 |  | Document implementation User Story 1 | 71.4 | 65
Document test User story 1 | 1.43 | 1 | 7.15 | 5 |  | Test User story 1 | 64.25 | 60
Document test User story 1 | 1.43 | 1 | 7.15 | 5 |  | Document test User story 1 | 57.1 | 55
Analysis User story 2 | 1.43 | 1 | 7.15 | 5 |  | Document test User story 1 | 49.95 | 50
Design Use story 2 | 1.43 | 1 | 7.15 | 5 |  | Analysis User story 2 | 42.8 | 45
Implement Use story 2 | 1.43 | 3 | 7.15 | 15 |  | Design Use story 2 | 35.65 | 40
Document implementation User Story 2 | 1.43 | 1 | 7.15 | 5 |  | Implement Use story 2 | 28.5 | 25
Test User story 2 | 1.43 | 1 | 7.15 | 5 |  | Document implementation User Story 2 | 21.35 | 20
Document test User story 2 | 1.43 | 1 | 7.15 | 5 |  | Test User story 2 | 14.2 | 15
Scrum Documentation Sprint 5 | 1.43 | 2 | 7.15 | 10 |  | Document test User story 2 | 7.05 | 10
Total | 20.02 | 20 | 100.1 | 100 |  | Scrum Documentation Sprint 5 | -0.1 | 0
If: | 20 | 100 |  | If: | 16 | 100
Then: | 3 | 15 |  | Then: | 2 | 12.5
If: | 16 | 100
Then: | 1 | 6.25

## Sprint 6
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: |  |  | Task: | Planned Effort: | Real Effort: | Done | 2 DAYS
Analysis User story 3 | 1.54 | 1 | 7.7 | 5 |  |  | Start | 100 | 100
Design Use story 3 | 1.54 | 1 | 7.7 | 5 |  |  | Analysis User story 3 | 92.3 | 95
Implement Use story 3 | 1.54 | 2 | 7.7 | 10 |  |  | Implement Use story 3 | 84.6 | 90
Document implementation User Story 3 | 1.54 | 2 | 7.7 | 10 |  |  | Design Use story 3 | 76.9 | 80
Test User story 3 | 1.54 | 0 | 7.7 | 0 |  |  | Document implementation User Story 3 | 69.2 | 70
Document test User story 3 | 1.54 | 0 | 7.7 | 0 |  |  | Test User story 3 | 61.5 | 70
Analysis User story 4 | 1.54 | 2 | 7.7 | 10 |  |  | Document test User story 3 | 53.8 | 70
Design User story 4 | 1.54 | 2 | 7.7 | 10 |  |  | Analysis User story 4 | 46.1 | 60
Implement Use story 4 | 1.54 | 1 | 7.7 | 5 |  |  | Design Use story 4 | 38.4 | 50
Document implementation User Story 4 | 1.54 | 1 | 7.7 | 5 |  |  | Implement Use story 4 | 30.7 | 45
Test User story 4 | 1.54 | 2 | 7.7 | 10 |  |  | Document implementation User Story 4 | 23 | 40
Document test User story 4 | 1.54 | 1 | 7.7 | 5 |  |  | Test User story 4 | 15.3 | 30
Scrum Documentation Sprint 6 | 1.54 | 2 | 7.7 | 10 |  |  | Document test User story 4 | 7.6 | 25
Total | 20.02 | 17 | 100.1 | 85 |  |  | Scrum Documentation Sprint 6 | -0.1 | 15
If: | 20 | 100 |  | If: | 16 | 100
Then: | 1 | 5 |  | Then: | 1.33 | 8.3125
If: | 16 | 100
Then: | 1.33 | 8.3125

## Sprint 7
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: | Task: | Planned Effort: | Real Effort: |  | 2 DAYS
Analysis User story 3 | 1.67 | 1 | 8.31 | 5 | Start | 100 | 100 | done
Design Use story 3 | 1.67 | 1 | 8.31 | 5 | Analysis User story 3 | 91.69 | 95
Test User story 3 | 1.67 | 2 | 8.31 | 10 | Design Use story 3 | 83.38 | 90
Document test User story 3 | 1.67 | 2 | 8.31 | 10 | Test User story 3 | 75.07 | 80
Analysis User story 5 | 1.67 | 2 | 8.31 | 10 | Document test User story 3 | 66.76 | 70
Design User story 5 | 1.67 | 2 | 8.31 | 10 | Analysis User story 5 | 58.45 | 60
Implement Use story 5 | 1.67 | 1 | 8.31 | 5 | Design Use story 5 | 50.14 | 50
Document implementation User Story 5 | 1.67 | 2 | 8.31 | 10 | Implement Use story 5 | 41.83 | 45
Test User story 5 | 1.67 | 2 | 8.31 | 10 | Document implementation User Story 5 | 33.52 | 35
Document test User story 5 | 1.67 | 2 | 8.31 | 10 | Test User story 5 | 25.21 | 25
Write Use Guide | 1.67 | 4 | 8.31 | 5 | Document test User story 5 | 16.9 | 15
Scrum Documentation Sprint 7 | 1.67 | 2 | 8.31 | 10 | Write Use Guide | 8.59 | 10
Total | 20.04 | 23 | 99.72 | 100 | Scrum Documentation Sprint 7 | 0 | 0
If: | 20 | 100
Then: | 1 | 5

## Sprint 8
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: | Task: | Planned Effort: | Real Effort: |  | 2 DAYS
Write Introduction section (Project report) | 2.5 | 1 | 12.5 | 5 | Start | 100 | 100 | done
Write Requirements section (Project Report) | 2.5 | 1 | 12.5 | 5 | Write Introduction section (Project report) | 87.5 | 95
Write Analysis section (Project Report) | 2.5 | 5 | 12.5 | 25 | Write Requirements section (Project Report) | 75 | 90
Write Introduction (Process report) | 2.5 | 1 | 12.5 | 5 | Write Analysis section (Project Report) | 62.5 | 65
Write Group description (Process report) | 2.5 | 1 | 12.5 | 5 | Write Introduction (Process report) | 50 | 60
Work in Appendix A | 2.5 | 2 | 12.5 | 10 | Write Group description (Process report) | 37.5 | 55
Work in Appendix B | 2.5 | 2 | 12.5 | 10 | Work in Appendix A | 25 | 45
Scrum Documentation Sprint 8 | 2.5 | 2 | 12.5 | 10 | Work in Appendix B | 12.5 | 35
Total | 20 | 15 | 100 | 75 | Scrum Documentation Sprint 8 | 0 | 25
If: | 20 | 100
Then: | 5 | 25

## Sprint 9
Task: | Planned Hours: | Real Hours: | Planned Effort: | Real Effort: | Task: | Planned Effort: | Real Effort: |  | 2 DAYS
Write Design section (Project Report) | 1.54 | 4 | 7.7 | 20 | Start | 100 | 100 | done
Write Implementation section (Project Report) | 1.54 | 4 | 7.7 | 20 | Write Design section (Project Report) | 92.3 | 80
Write Test section (Project Report) | 1.54 | 3 | 7.7 | 15 | Write Implementation section (Project Report) | 84.6 | 60
Write Conclusion section (Project Report) | 1.54 | 2 | 7.7 | 10 | Write Test section (Project Report) | 76.9 | 45
Write abstract (Project Report) | 1.54 | 1 | 7.7 | 5 | Write Conclusion section (Project Report) | 69.2 | 35
Write Project Initiation section(Process report) | 1.54 | 2 | 7.7 | 10 | Write abstract (Project Report) | 61.5 | 30
Write Project Description section (Process report) | 1.54 | 2 | 7.7 | 10 | Write Project Initiation section(Process report) | 53.8 | 20
Write Project Execution section(Process report) | 1.54 | 3 | 7.7 | 15 | Write Project Description section (Process report) | 46.1 | 10
Write Personal Reflections section(Process report) | 1.54 | 5 | 7.7 | 25 | Write Project Execution section(Process report) | 38.4 | -5
Write Conclusion (Process report) | 1.54 | 2 | 7.7 | 10 | Write Personal Reflections section(Process report) | 30.7 | -30
Work in Appendix A | 1.54 | 3 | 7.7 | 15 | Write Conclusion (Process report) | 23 | -40
Work in Appendix B | 1.54 | 3 | 7.7 | 15 | Work in Appendix A | 15.3 | -55
Scrum Documentation Sprint 9 | 1.54 | 2 | 7.7 | 10 | Work in Appendix B | 7.6 | -70
Total | 20.02 | 36 | 100.1 | 180 | Scrum Documentation Sprint 9 | -0.1 | -80
If: | 20 | 100
Then: | 1.54 | 7.7

## Sprint 10
Task: | Planned Effort: | Real Effort: | 2 DAYS

## TOTAL
| Sprints (hours) | Planned effort | Real Effort |  | Planned effort | Real Effort |  | 61 DAYS
start: | 0 | 1000 | 1000 | 0 | 1000 | 1000
Sprint 1 finished | 100 | 900 | 940 | 10 | 979.17 | 994
Sprint 2 finished | 200 | 800 | 940 | 20 | 958.34 | 988
Sprint 3 finished | 300 | 700 | 830 | 30 | 937.51 | 982
Sprint 4 finished | 350 | 600 | 700 | 40 | 916.68 | 976
Sprint 5 finished | 370 | 500 | 580 | 50 | 895.85 | 970
Sprint 6 finished | 390 | 400 | 460 | 60 | 875.02 | 964
Sprint 7 finished | 410 | 300 | 340 | 70 | 854.19 | 958
Sprint 8 finished | 440 | 200 | 265 | 80 | 833.36 | 952
Sprint 9 finished | 460 | 100 | 85 | 90 | 812.53 | 946
Sprint 10 finished | 480 | 0 | 25 | 100 | 791.7 | 940 | 6
|  |  |  | 110 | 770.87 | 940
|  |  |  | 120 | 750.04 | 940
|  |  |  | 130 | 729.21 | 940
|  |  |  | 140 | 708.38 | 940
|  |  |  | 150 | 687.55 | 940
|  |  |  | 160 | 666.72 | 940
|  |  |  | 170 | 645.89 | 940
|  |  |  | 180 | 625.06 | 940
|  |  |  | 190 | 604.23 | 940
|  |  |  | 200 | 583.4 | 940
|  |  |  | 210 | 562.57 | 929
|  |  |  | 220 | 541.74 | 918
|  |  |  | 230 | 520.91 | 907
|  |  |  | 240 | 500.08 | 896
|  |  |  | 250 | 479.25 | 885
|  |  |  | 260 | 458.42 | 874
|  |  |  | 270 | 437.59 | 863
|  |  |  | 280 | 416.76 | 852
|  |  |  | 290 | 395.93 | 841
|  |  |  | 300 | 375.1 | 830 | 11
|  |  |  | 310 | 354.27 | 804
|  |  |  | 320 | 333.44 | 778
|  |  |  | 330 | 312.61 | 752
|  |  |  | 340 | 291.78 | 726
|  |  |  | 350 | 270.95 | 700 | 26
|  |  |  | 360 | 250.12 | 640
|  |  |  | 370 | 229.29 | 580 | 60
|  |  |  | 380 | 208.46 | 520
|  |  |  | 390 | 187.63 | 460 | 60
|  |  |  | 400 | 166.8 | 400
|  |  |  | 410 | 145.97 | 340 | 60
|  |  |  | 420 | 125.14 | 315
|  |  |  | 430 | 104.31 | 290
|  |  |  | 440 | 83.48 | 265 | 25
|  |  |  | 450 | 62.65 | 175
|  |  |  | 460 | 41.82 | 85 | 90
|  |  |  | 470 | 20.99 | 55
|  |  |  | 480 | 0.16 | 25 | 30